## Agile Journey
Organization or team:
| Current Level | Target Level | Traditional (T) | Near (N) | Basic (B) | Intermediate (I) | Advanced (A) | Examples | Condition
Primary Measures
Cycle Time (see definition below) |  |  | Year or more | Quarter | 4 weeks | 2 weeks | 1 day | Scrum, 2 week iterations
Customer involvement |  |  | Infrequent | Feedback on completed work at least once every four weeks from real users of the solution or a reasonable proxy | Feedback on completed work at least once every two weeks from real users of the solution or a reasonable proxy | Feedback on completed work at least once per week from real users of the solution or a reasonable proxy | Continuous involvement of real users of the solution | Iteration review, product owner, user voice, survey monkey, instrumentation, built-in feedback mechanisms
Quality |  |  | No definition of done | Steps are being actively taken to move to the basic level | There is a definition of done. Steps are being taken to automate all testing and deployment activities. | The definition of done was agreed to by most parties responsible for getting work to done and it is generally followed. | The definition of done was agreed to by all parties and it is strictly followed. All testing and deployment is automated to the point of continuous deployment. | TDD, CI, CD
Morale |  |  | Not yet at the basic level and there is no move in that direction | Steps are being actively taken to move to the basic level | People feel like their work is part of a shared goal. | People have some choice in what they work in, deciding how to accomplish the work, and in determining the amount of effort required to complete it. | People are happy, supported, trusted, safe, and feel a sense of purpose, they feel it is one of the best places they have ever worked
Secondary Measures
Funding / approval of work |  |  | Year or more | Quarterly | 4 weeks or less | 2 weeks or less | Continuous | Kanban, product owner, value stream
Inspect and adapt |  |  | None | Infrequent | 4 weeks | 2 weeks or less | Continuous | Retrospective every 2 weeks, stop the line (continuous) | When everyone involved in the organizational unit is part of the activity and changes are made as a result
WIP (per person, across all of that person's projects/teams) |  |  | Unknown | Known | 5 | 3 | 1 or 2
Typical time it takes to get the information needed to complete work |  |  | More than 4 weeks | Within 4 weeks | Within 1 week | Within 1 day | Within an hour | Scrum stand-up meeting, co-located team
Breaking work down |  |  | Not yet at the near level | At least one item done start to finish per person every four weeks | At least one item done start to finish every two weeks | At least one item done start to finish per person per week | Continuous value | Story splitting, use of INVEST, user stories, agile estimation, vertical slicing | Per person means per person involved in getting work from start to finish. Example: for an 8 person scrum team using user stories, intermediate would mean that as a team they complete 8 user stories per week
Well understood process |  |  | Not yet at the near level | Steps are being actively taken to move to the basic level | The process of how work flows from customer to production are well understood by the people for their pieces of the process | Most of the process of how work flows from customer to production are covered by consensus based agreements | All aspects of the flow of work from customer to production are covered in consensus based agreements | Team working agreement, definition of ready, definition of done, user stories
Copyright 2018 Damon B. Poole. All rights reserved. Permission to freely use and re-distributed as long as this notice is included and the content is not modified. Content may adated for use within an organization.

## Notes
Organizational unit | Organizational unit refers to the group of people being considered. For instance, it could be a Scrum team, or the people associated with a Kanban board, or everyone within product development.
Cycle time | In this document, the cycle time refers by default to the time it takes for a user request to get from the user into production. It must be along an official path, which means it must be documented and not part of any expidited or exception based process. Also, if work must be part of a funded project, then either there is an official way to add an important new item and the full time for that process must be included or the full time it takes to get a project funded must be included.